## Resourse Usage Baseline
Name | Resource | Units | Baseline Work | Baseline Cost | Rates | Units
Human |  |  | 792 | 65640
Harrington |  |  | 96 | 8160 | 85 | Hour
Cost & Effort Estimate | Harrington |  | 40 | 3400
Final Report | Harrington |  | 8 | 680
Formulate Initial Team Roles | Harrington |  | 4 | 340
Draft & Authorise Project Charter | Harrington |  | 24 | 2040
Project Deployment | Harrington |  | 8 | 680 |  |  | Note: Add Actuals once project completed.
Identify Project Stakeholders | Harrington |  | 4 | 340
Develop Business Case & NPV | Harrington |  | 8 | 680
Anas |  |  | 152 | 11400 | 75 | Hour
Project Scope | Anas |  | 40 | 3000
[FR-02] Tiered Eligibility | Anas |  | 16 | 1200
Functional Testing | Anas |  | 16 | 1200
Cost & Effort Estimate | Anas |  | 20 | 1500
Formulate Initial Team Roles | Anas |  | 8 | 600
Final Report | Anas |  | 8 | 600
Performance & Accessibility Checks | Anas |  | 8 | 600
WBS & Dictionary | Anas |  | 20 | 1500
Staff Training | Anas |  | 8 | 600
Develop Business Case & NPV | Anas |  | 8 | 600
Denisha |  |  | 160 | 12000 | 75 | Hour
UI/UX Wireframe & Style Guide | Denisha |  | 80 | 6000
[FR-07] QR Verification/Generation | Denisha |  | 16 | 1200
[FR-01] Identity & Access | Denisha |  | 16 | 1200
Final Report | Denisha |  | 8 | 600
Staff Training | Denisha |  | 8 | 600
Formulate Initial Team Roles | Denisha |  | 8 | 600
[FR-04] Booking Lifecycle | Denisha |  | 24 | 1800
Adam |  |  | 304 | 28880 | 95 | Hour
[FR-01] Identity & Access | Adam |  | 16 | 1520
[FR-06] Payment Processing | Adam |  | 16 | 1520
Development Environment | Adam |  | 8 | 760
Pen Testing/ Bug Fixing | Adam |  | 16 | 1520
Functional Testing | Adam |  | 16 | 1520
[FR-07] QR Verification/Generation | Adam |  | 16 | 1520
[FR-02] Tiered Eligibility | Adam |  | 16 | 1520
[FR-04] Booking Lifecycle | Adam |  | 24 | 2280
[FR-03] Six-Month Gate | Adam |  | 16 | 1520
Performance & Accessibility Checks | Adam |  | 8 | 760
Database Schema Design | Adam |  | 40 | 3800
Project Deployment | Adam |  | 8 | 760
Formulate Initial Team Roles | Adam |  | 8 | 760
Database Seeding | Adam |  | 8 | 760
System Architecture Design | Adam |  | 40 | 3800
[FR-05] Occupancy Logic | Adam |  | 24 | 2280
Final Report | Adam |  | 8 | 760
[FR-8] Data Management | Adam |  | 16 | 1520
Finley |  |  | 80 | 5200 | 65 | Hour
Final Report | Finley |  | 8 | 520
Project Deployment | Finley |  | 8 | 520
Risk Registry | Finley |  | 40 | 2600
Pen Testing/ Bug Fixing | Finley |  | 16 | 1040
Identify Project Stakeholders | Finley |  | 4 | 260
Formulate Initial Team Roles | Finley |  | 4 | 260
Other |  |  | 0 | 104700
Development Environment |  |  | 0 | 20000 | 20000 | Each
Development Environment | Development Environment | 1 | 0 | 20000
Production Hosting |  |  | 0 | 15000 | 15000 | Yearly
Project Deployment | Production Hosting | 1 | 0 | 15000
Domain & SSL - Yearly |  |  | 0 | 500 | 500 | Yearly
Project Deployment | Domain & SSL - Yearly | 1 | 0 | 500
Mock Flight Schedule API |  |  | 0 | 12000 | 12000 | Each
Development Environment | Mock Flight Schedule API | 1 | 0 | 12000
QR Code Scanners |  |  | 0 | 3200 | 800 | Each
Project Deployment | QR Code Scanners | 4 | 0 | 3200
Self-Service Kiosks |  |  | 0 | 24000 | 6000 | Each
Project Deployment | Self-Service Kiosks | 4 | 0 | 24000
Contingency Fund |  |  | 0 | 10000 | 10000 | Each
Draft & Authorise Project Charter | Contingency Fund | 1 | 0 | 10000
Security Audit |  |  | 0 | 15000 | 15000 | Each
Pen Testing/ Bug Fixing | Security Audit | 1 | 0 | 15000
Legal & Compliance |  |  | 0 | 5000 | 5000 | Each
Project Deployment | Legal & Compliance | 1 | 0 | 5000
Total |  |  |  | 170340

## WBS Dictionary
Code | Deliverable Name | Description of Work | Resources Assigned (Labor) | Material / Non-Labor Costs | Effort (Hrs) | Cost (A$) | Acceptance Criteria
| FlyDreamAir: Lounge Management System | Overall project to develop a Lounge Management System for FlyDreamAir. | - | - | 792 | 170340 | Final system meets all functional requirements and is accepted by the client.
1 | Phase: Initialization | Starting phase to establish foundation and assign initial responsibilities. | - | - | 80 | 16480 | Completion and approval of all phase 1 documentation.
1.1 | Formulate Initial Team Roles | Define team roles and responsibilities to ensure each member understands tasks. | All | - | 32 | 2560 | Signed roles and responsibilities matrix.
1.2 | Identify Project Stakeholders | Identify internal and external stakeholders who influence or are affected. | Harrington; Finley | - | 8 | 600 | Stakeholder register identifying power and interest levels.
1.3 | Develop Business Case & NPV | Prepare business case including benefits, financial analysis, and NPV. | Harrington; Anas | - | 16 | 1280 | Approved business case with positive NPV.
1.4 | Draft & Authorize Project Charter | Define project objectives, scope, stakeholders, and authority to proceed. | Harrington | Contingency Fund | 24 | 12040 | Charter signed and authorized by project sponsor.
1.5 | Milestone: Project Authorisation
2 | Phase: Planning | Planning phase where boundaries, risks, costs, and structure are defined. | - | - | 160 | 12000 | Baseline project plan approved.
2.1 | Project Scope | Define project boundaries, key features, inclusions, and exclusions. | Anas | - | 40 | 3000 | Formally accepted Project Scope Statement.
2.2 | WBS & Dictionary | Break project into manageable packages and provide definitions. | Anas | - | 20 | 1500 | WBS hierarchy matches Gantt chart structure.
2.3 | Risk Registry | Identify potential risks and record likelihood, impact, and response. | Finley | - | 40 | 2600 | Risk register with categorized impacts and mitigations.
2.4 | Cost & Effort Estimate | Estimate budget, resource effort, and time required for completion. | Harrington; Anas | - | 60 | 4900 | Final budget aligned with Resource Usage view.
2.5 | Milestone: Scope Approval
3 | Phase: Design | Phase where system designs are prepared before development begins. | - | - | 160 | 13600 | Completion of database, UI, and architecture specs.
3.1 | Database Schema Design | Design database structure for user accounts, bookings, and lounge ops. | Adam | - | 40 | 3800 | ERD and schema supporting all data requirements.
3.2 | UI/UX Wireframe & Style Guide | Design interface layout and visual style for staff and passengers. | Denisha | - | 80 | 6000 | Verified wireframes for all major system screens.
3.3 | System Architecture Design | Define technical structure, modules, and component interactions. | Adam | - | 40 | 3800 | Documented architecture and technology stack.
3.4 | Milestone: Design Approval
4 | Phase: Development |  |  |  | 232 | 52600
4.1 | Sprint Setup: Infrastructure
4.1.1 | Development Environment | Configure tools, repository, framework, and working environment. | Adam | Dev Env; Mock Flight API | 8 | 32760 | GitHub repo active and development tools installed.
4.1.2 | Database Seeding | Insert sample data to support testing and prototype demonstration. | Adam | - | 8 | 760 | Database populated with functional test data.
4.2 | Sprint 1: Foundation
4.2.1 | [FR-01] Identity & Access | Develop authentication and access control for staff/passengers. | Denisha; Adam | - | 32 | 2720 | Secure login and role-based access verified.
4.2.2 | [FR-08] Data Management | Implement functions for storing, retrieving, and updating data. | Adam | - | 16 | 1520 | CRUD operations for core data entities functional.
4.3 | Sprint 2: Core Logic
4.3.1 | [FR-02] Tiered Eligibility | Implement membership tier validation (Blue and Gold). | Adam; Anas | - | 32 | 2720 | Correct tier assignment based on usage logic.
4.3.2 | [FR-03] Six-Month Gate | Implement rule for 6-month account age for pay-per-use eligibility. | Adam | - | 16 | 1520 | Access restricted for accounts under 180 days old.
4.3.3 | [FR-05] Occupancy Logic | Develop logic for lounge capacity, occupancy, and availability. | Adam | - | 24 | 2280 | System correctly calculates and displays occupancy.
4.4 | Sprint 3: Transactional Functions
4.4.1 | [FR-04] Booking Lifecycle | Implement booking creation, modification, and cancellation. | Denisha; Adam | - | 48 | 4080 | End-to-end booking flow functional and tested.
4.4.2 | [FR-06] Payment Processing | Develop pay-per-use payment handling process. | Adam | - | 16 | 1520 | Payment transaction records successfully generated.
4.4.3 | [FR-07] QR Verification/Generation | Implement QR generation and verification for entry validation. | Denisha; Adam | - | 32 | 2720 | QR codes generated and validated by scanner logic.
4.5 | Milestone: Development Complete
5 | Phase: Testing / Q&A |  |  |  | 80 | 21640
5.1 | Functional Testing | Test all system functions against project requirements. | Anas; Adam | - | 32 | 2720 | All functional requirements pass verification.
5.2 | Performance & Accessibility Checks | Evaluate responsiveness, usability, and accessibility standards. | Anas; Adam | - | 16 | 1360 | UI meets defined responsiveness and accessibility goals.
5.3 | Pen Testing/ Bug Fixing | Identify security issues and bugs; correct before deployment. | Adam; Finley | Security Audit | 32 | 17560 | Critical bugs resolved and security audit completed.
5.4 | Milestone: Testing Complete
6 | Phase: Closing |  |  |  | 80 | 54020
6.1 | Project Deployment | Deploy final prototype for demonstration or implementation. | Adam; Harrington; Finley | Hosting; SSL; Scanners; Kiosks; Legal | 24 | 49660 | System live on hosting environment with hardware.
6.2 | Staff Training | Provide guidance to staff on using the new system. | Anas; Denisha | - | 16 | 1200 | Training completed and user documentation delivered.
6.3 | Final Report | Compile and submit final report documenting conclusions. | Harrington; Anas; Denisha; Adam; Finley | - | 40 | 3160 | Final report submitted and accepted on Moodle.
6.4 | Milestone: Project Complete

## Cocomo II
Scale Factors
Scale Factor | Rating | Score
PREC (Precedentedness) | Low | 4.96 |  | Estimated | Actual | Variance
FLEX (Flexibility) | V. High | 1.21 | Kloc | 2
RESL (Architecture/Risk) | V. High | 1.41 | Estimated Effort (Person-Month) | 4.4372 | 5.2105
TEAM (Cohesion) | Nominal | 3.29 | Total Labor Hours | 674.4562 | 792 | 14.84%
PMAT (Maturity) | High | 3.12
Total sum |  | 13.99
Scale Factor |  | 1.0499
Effort Multipliers
Driver | Rating | Value
RCPX (Complexity/Reliability) | High | 1.33
PERS (Personnel Capability) | V. High | 0.63
PREX (Personnel Experience) | Nominal | 1
FCIL (Facilities/Tools) | High | 0.87
SCED (Schedule) | Nominal | 1
Total Product |  | 0.72897

## Function Point Analysis
Component | Description | Count | Complexity | Weight | Total | Degree of Influence
ILF (Internal Logical Files) | Tables you maintain: Users, Tiers, Bookings, Tenants, Products. | 5 | Low | 7 | 35 | Characteristic | Rating
EIF (External Interface Files) | External data you read: Stripe Payment Status, Social Media Feeds. | 2 | Low | 5 | 10 | Data Communications | 5
EI (External Inputs) | Forms/Data entering: User Registration, Booking Creation, Tier Updates. | 8 | Med | 4 | 32 | Distributed Data | 4
EO (External Outputs) | Calculated data leaving: Invoice Generation, Analytics Dashboard, QR Code. | 4 | Med | 5 | 20 | Performance | 4
EQ (External Inquiries) | Data retrieval (no calc): Check Occupancy, View Profile, Search Items. | 6 | Low | 3 | 18 | Heavily Used Config | 3
Total Unadjusted FP |  |  |  |  | 115 | Transaction Rate | 3
Total Adjusted Function Points |  |  |  |  | 134.55 | Online Data Entry | 5
[6 empty] | End-User Efficiency | 4
[6 empty] | Online Update | 4
[6 empty] | Complex Processing | 4
[6 empty] | Reusability | 3
[6 empty] | Installation Ease | 2
[6 empty] | Operational Ease | 3
[6 empty] | Multiple Sites | 5
[6 empty] | Facilitate Change | 3
[6 empty] | Total Degree of Influence | 52
[6 empty] | Value Adjustment Factor | 1.17

## Financial Analysis
Discount Rate |  |  |  | 8%
| Year |  |  | Total
| 0 | 1 | 2
Costs | 170340 | 15500 | 15500
Discount Factor | 1 | 0.92593 | 0.85734
Discounted Costs | 170340 | 14351.8519 | 13288.7517 | 197980.6036
Benefits | 1733750 | 1733750 | 1733750
Discount Factor | 1 | 0.92593 | 0.85734
Discounted Benefits | 1733750 | 1605324.0741 | 1486411.1797 | 4825485.2538
Discounted Benefits - Costs | 1563410 | 1590972.2222 | 1473122.428
Cumulative Benefits - Costs | 1563410 | 3168734.0741 | 4655145.2538
Discounted Lifecycle ROI |  |  |  | 2337%
Assumptions
Cost Breakdown
Human Labor | 65640
Materials | 104700
Total Costs | 170340
Benefits Breakdown
Lounge Passes | 1186250
Food & Beverage | 547500
Total Benefits | 1733750
On-Going Costs
Hosting | 15000
Domain + SSL | 500
Total On-Going | 15500